## Sheet1
Task | Owner | Assistant | Start plan date | Finish plan date
Test spec and report form writing | MarCar | ChrAta | 2020-07-21 | 2020-07-22
Techical review test spec | ChrAta | MarCar, RemLac | 2020-07-22 | 2020-07-22
Test spec Doc and Q&R Review | DavKuh, LynTho | MarCar | 2020-07-22 | 2020-07-23
Create test Report 1.1 empty doc | DavKuh |  | 2020-07-22 | 2020-07-23
Test run | MarCar | ChrAta | 2020-07-24 | 2020-07-24
Test report writing | MarCar |  | 2020-07-24 | 2020-07-24
Test report technical review / conclusion | ChrAta, RemLac | MarVer | 2020-07-24 | 2020-07-27
Test report Doc and Q&R Review | DavKuh, LynTho | MarCar | 2020-07-27 | 2020-07-28
ECR push | TemBol |  | 2020-07-28 | 2020-07-30